## Tabelle1
Featureplan:

READY	Feature Ready	---	Not used
05/2016	Feature Planned	???	Not planned

ServiceSet	Function	Client				Server
		OPC UA Interface		Value Based Interface		Information Model	OPC UA Interface		Value Based Interface
		Sync	Async	Sync	Async		Sync	Async	Sync	Async
Discover	FindServer	05/2016	05/2016	---	---	05/2016	05/2016	05/2016	---	---
	GetEndpoints	READY	READY	---	---	READY	05/2016	05/2016	---	---
	RegisterServer	05/2016	05/2016	---	---	05/2016	05/2016	05/2016	---	---
Secure	OpenSecureChannel	READY	READY	READY	READY	READY	???	???	---	---
	CloseSecureChannel	READY	READY	READY	READY	READY	???	???	---	---
Session	CreateSession	READY	READY	READY	READY	READY	???	???	---	---
	ActivateSession	READY	READY	READY	READY	READY	???	???	---	---
	CloseSession	READY	READY	READY	READY	READY	???	???	---	---
	Cancel	READY	READY	04/2016	04/2016	04/2016	???	???	---	---
Node Management	AddNodes	READY	READY	04/2016	04/2016	03/2016	04/2016	04/2016	---	---
	AddReferences	READY	READY	04/2016	04/2016	03/2016	04/2016	04/2016	---	---
	DeleteNodes	READY	READY	04/2016	04/2016	03/2016	04/2016	04/2016	---	---
	DeleteReferences	READY	READY	04/2016	04/2016	03/2016	04/2016	04/2016	---	---
View	Browse	READY	READY	---	---	READY	???	???	---	---
	BrowseNext	READY	READY	---	---	READY	???	???	---	---
	TranslateBrowsePaths	READY	READY	04/2016	04/2016	04/2016	???	???	---	---
	RegisterNodes	04/2016	04/2016	04/2016	04/2016	04/2016	???	???	---	---
	UnregisterNodes	04/2016	04/2016	04/2016	04/2016	04/2016	???	???	---	---
Query	QuerryFirst	READY	READY	---	---	---	---	---	---	---
	QueryNext	READY	READY	---	---	---	---	---	---	---
Attribute	Read	READY	READY	READY	READY	READY	02/2016	02/2016	READY	02/2016
	HistoryRead	READY	READY	03/2016	03/2016	03/2016	03/2016	03/2016	03/2016	03/2016
	Write	READY	READY	READY	READY	READY	02/2016	02/2016	READY	02/2016
	HistoryUpdate	READY	READY	03/2016	03/2016	03/2016	03/2016	03/2016	03/2016	03/2016
Method	Call	READY	READY	02/2016	02/2016	02/2016	02/2016	02/2016	02/2016	02/2016
Monitored Item	CreateMonitoredItem	READY	READY	READY	READY	READY	???	???	---	---
	ModifyMonitoredItem	READY	READY	03/2016	03/2016	03/2016	???	???	---	---
	SetMonitoringMode	READY	READY	03/2016	03/2016	03/2016	???	???	---	---
	SetTriggering	READY	READY	03/2016	03/2016	03/2016	???	???	---	---
	DeleteMonitotedItems	READY	READY	READY	READY	READY	???	???	---	---
Subscription	CreateSubscription	READY	READY	READY	READY	READY	???	???	---	---
	ModifySubscription	READY	READY	04/2016	04/2016	04/2016	???	???	---	---
	Publish/Set	READY	READY	READY	READY	READY	READY	02/2016	READY	02/2016
	Republish	04/2016	04/2016	04/2016	04/2016	04/2016	???	???	???	???
	TransferSubscription	04/2016	04/2016	04/2016	04/2016	04/2016	???	???	???	???
	DeleteSubscription	READY	READY	READY	READY	READY	???	???	???	???
Security	SecureChannel	06/2016				06/2016
	User	06/2016				06/2016
	Certificates	02/2016				02/2016

Client:
OPC UA Interface		Contains the OPC UA interface with full functionality. To use the interface OPC UA skills are necessary.
Value Based Interface		Contains a value based interface with limited functionality. To use the interface OPC UA skills are not necessary.

Server:
Information Model		Interface of the OPC UA information model of the OPC UA Server
OPC UA Interface		OPC UA Applications are deployed to the OPC UA Server in form of libraries. The OPC UA Interface contains the full OPC UA functionality. To use the interface OPC UA skills are necessary.
Value Based Interface		OPC UA Applications are deployed to the OPC UA Server in form of libraries. The value based Interface contains the limited OPC UA functionality. To use the interface OPC UA skills are not necessary.